## Sheet1 (hidden)
# | Column Name | Remarks
A | Req ID | Every requirement should have a requirement #
B | Proposed By | User who proposes the requirement
C | Proposed date | MM/DD/YYYY
D | Requirement Name | What business needs based on features, functionalities, data, integration, request and responses, etc.
E | Requirement Description | Detail description of the requirements
F | Facilitator | Person who conducts the requirements gathering from the users.
G | Scriber | Person who documents the requirement.
H | Application
I | Module
J | Screen
K | Project Scope (Y/N)
L | Release/ Phase
M | LOE | Level of effort
N | Priority Level (H/M/L)
O | Risk Level (H/M/L)
P | BA Owner
Q | SME Owner
R | DEV Owner
S | GAP (Y/ N)
T | GAP Description
U | Requirement Type
V | Requirement Sub- Type
W | Requirement Status
X | Approved By
Y | Approved Date | MM/DD/YYYY
Z | Use Case ID
AA | BRD ID
AB | FSD/ FRD ID
AC | TDD ID | Created by developer
AD | Error ID
AE | Message Id
AF | Business Rule ID
AG | Interface ID
AH | Test scenario ID | Created by Testing Team
AI | Test Case ID | Created by Testing Team
AJ | Test Execution Status | Created by Testing Team
AK | Defect ID | Project Team
AL | Defect Status | Project Team
AM | Defect Priority | Project Team
AN | Issue Log ID | BA
AO | Change Request ID | BA
AP | Change Request Status | BA
AQ | Document Location | BA/ Project Team
AR | Remarks/ Comments | Every comment will have the date and time stamp –
Example –
[DP- 10/25/2023- 02:25:00 PM PST] – needs more inputs from dev team.

## Sheet2
Column Name | Req ID | Proposed By | Proposed date | Requirement Name | Requirement Description | Facilitator | Scriber | Application | Module | Screen | Project Scope (Y/N) | Release/ Phase | LOE | Priority Level (H/M/L) | Risk Level (H/M/L) | BA Owner | SME Owner | DEV Owner | GAP (Y/ N) | GAP Description | Requirement Type | Requirement Sub- Type | Requirement Status | Approved By | Approved Date | Use Case ID | BRD ID | FSD/ FRD ID | TDD ID | Error ID | Message Id | Business Rule ID | Interface ID | Test scenario ID | Test Case ID | Test Execution Status | Defect ID | Defect Status | Defect Priority | Issue Log ID | Change Request ID | Change Request Status | Document Location | Remarks/ Comments
1 | REQ-110823-RSC-MAIN-FT-1.1 | Liza Doolittle | 2023-11-21 | Users should be able to create accounts securely | The system should have an option for users to create/modify an account on the main web screen | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 2 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-11-28
2 | REQ-110823-RSC-MAIN-FT-1.2 | Liza Doolittle | 2023-11-21 | User profiles should allow for the addition of health information, emergency contacts, and medication details | The system should have the option to add additional user information such as health information, Contacts, etc. | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 3 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-11-29
3 | REQ-110823-RSC-MAIN-FT-1.3 | Liza Doolittle | 2023-11-21 | Users should access the medication reminders and other reminders with saved medicines option. | The system should have the option for setting medication reminder and add required medicines. | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Reminders | Y | R1/PH-1 | 6 Hrs | L | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-11-30
4 | REQ-110823-RSC-MAIN-FT-1.4 | Liza Doolittle | 2023-11-21 | Users should be able to record and monitor daily activities, exercise routines, and nutritional intake | The system should have the option for tracking user daily records such as activities, exercise routines, nutrition | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Reminders | N | R1/PH-1 | 5 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-01
5 | REQ-110823-RSC-MAIN-FT-1.5 | Liza Doolittle | 2023-11-21 | Users should access the Integration with telehealth services to consult healthcare professionals remotely | The healthcare professionals are listed on the telehealth integration page for users to connect. | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-2 | 4 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | Y | Telehealth Services need to be consulted for the integration | Functional | Functionality | Approved | Olive Yew | 2023-12-02
6 | REQ-110823-RSC-MAIN-FT-1.6 | Liza Doolittle | 2023-11-21 | User should be able to Schedule and conduct video or chat consultations with doctors, specialists, or healthcare providers | The Video or text chat features for user to book appointments With a doctors specialist and healthcare providers | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-2 | 6 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | Y | The listed people should be consulted with the app for appointments | Functional | Functionality | Approved | Olive Yew | 2023-12-03
7 | REQ-110823-RSC-MAIN-FT-1.7 | Liza Doolittle | 2023-11-21 | Users should see pharmacy options for prescription refills and deliveries | The web page has pharmacy options for users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Pharmacy | Y | R1/PH-2 | 7 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-04
8 | REQ-110823-RSC-MAIN-FT-1.8 | Liza Doolittle | 2023-11-21 | Users should be able to access to a library of health-related articles, tips, and resources specifically tailored for seniors | The web page has integrated library that can show the health-related articles tips resources that specified for the seniors | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Health-related | Y | R1/PH-2 | 4 Hrs | L | H | Mary Magdalene | Allie Grater | Teri Dactyl | Y | The listed resources need to be consulted first inorder to showcase them online | Functional | Functionality | Approved | Olive Yew | 2023-12-05
9 | REQ-110823-RSC-MAIN-FT-1.9 | Liza Doolittle | 2023-11-21 | Users should see video tutorials or guides for exercises, healthy living, or managing specific health conditions | There are some videos guides and tutorials available for access for users to exercise and healthy living in managing specific related to health conditions | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Health-related | Y | R1/PH-2 | 6 Hrs | L | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-06
10 | REQ-110823-RSC-MAIN-FT-1.10 | Liza Doolittle | 2023-11-21 | Users should interact with a Simple and intuitive user interface with large fonts, clear icons, and navigation suitable for seniors | The website has simple and intuitive user interface which has various options like enlarge fonts clear icons and easily navigation | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-1 | 7 Hrs | H | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-07
11 | REQ-110823-RSC-MAIN-FT-1.11 | Liza Doolittle | 2023-11-21 | Users should access different entertainment options nearby their locations | The showcase of the different entertainment options nearby to users' locations for user to enjoy | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Entertainment | Entertainment | Y | R1/PH-2 | 3 Hrs | L | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-08
12 | REQ-110823-RSC-MAIN-FT-1.12 | Liza Doolittle | 2023-11-22 | Users should access accessibility, ease of use and various support option | The support options are available for easy access and ease of use for users to use the application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Contact Us | Contact Us | Y | R1/PH-2 | 6 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-09
13 | REQ-110823-RSC-TRANS-2.1 | Liza Doolittle | 2023-11-22 | Users should be able to create and manage profiles for themselves and the seniors they are caring for | The system has option for create and manage profile for themselves and the seniors they are caring for | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-2 | 5 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-10
14 | REQ-110823-RSC-TRANS-2.2 | Liza Doolittle | 2023-11-22 | Users should be able to schedule appointments for medical check-ups, caregiver visits, and other related services | The system has features for setting up an appointment for medical checkups caregivers visitors and other related services for users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 4 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-11
15 | REQ-110823-RSC-TRANS-2.3 | Liza Doolittle | 2023-11-22 | Users should have the ability to request various services such as home healthcare, transportation, and meal deliveries | The system has various services listed on the application such as home health transportation and middle leverage for users to easily access | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 6 Hrs | L | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2023-12-12
16 | REQ-110823-RSC-TRANS-2.3.1 | Liza Doolittle | 2023-11-22 | Service requests should include details like date, time, and specific requirements | The system has options for selecting date time and specific requirements for requesting those services | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 7 Hrs | L | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-13
17 | REQ-110823-RSC-TRANS-2.3.2 | Liza Doolittle | 2023-11-22 | Upon selecting and scheduling a service, users should receive confirmation notifications. | The system should send a confirmation notification via email or text to the user upon selecting and scheduling services | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 4 Hrs | L | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-14
18 | REQ-110823-RSC-TRANS-2.4 | Liza Doolittle | 2023-11-22 | The app should support secure payment processing for any paid services or transactions | The system has the secure payment processing for any paid service and transaction | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health, Telehealth Integration | Payment | Y | R1/PH-1 | 3 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-15
19 | REQ-110823-RSC-TRANS-2.4.1 | Liza Doolittle | 2023-11-22 | Multiple payment options should be available, including credit cards and digital wallets | The payment gateway has the different credit card and digital wallet options for users to add and support multiple payment options | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health, Telehealth Integration | Payment | Y | R1/PH-2 | 6 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-16
20 | REQ-110823-RSC-TRANS-2.5 | Liza Doolittle | 2023-11-22 | For recurring services, the website should support subscription-based models | The website should have subscription based models for users to recur the services | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health, Telehealth Integration | Payment | N | R1/PH-3 | 5 Hrs | L | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-17
21 | REQ-110823-RSC-TRANS-2.6.1 | Liza Doolittle | 2023-11-22 | For care givers, Receive service requests and confirm availability | The system should be able to send and accept requests for caregivers and confirm their availability | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 4 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-18
22 | REQ-110823-RSC-TRANS-2.6.2 | Liza Doolittle | 2023-11-22 | For care givers, Access detailed service information | The system should show the detailed service information about the caregivers upon receiving service request | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Telehealth | Y | R1/PH-1 | 6 Hrs | M | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-19
23 | REQ-110823-RSC-TRANS-2.7 | Liza Doolittle | 2023-11-23 | All sensitive user information, including payment details, should be encrypted | The system uses advanced encrypted method for all sensitive user information | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 7 Hrs | H | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-20
24 | REQ-110823-RSC-TRANS-2.8 | Liza Doolittle | 2023-11-23 | Utilize secure and reputable payment gateways to process financial transactions | The website has secured and represented payment gateway for financial transaction | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 4 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-21
25 | REQ-110823-RSC-TRANS-2.9 | Liza Doolittle | 2023-11-23 | Implement analytics to track user behavior, popular services, and transaction trends | The system should implement advanced analytical software to track user behavior and popular services and transaction trends based on each users behavior | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 3 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-22
26 | REQ-110823-RSC-TRANS-2.10 | Liza Doolittle | 2023-11-23 | Provide a support system for users to address transaction-related issues | The system has options for users to report the transaction related issues and other issues related to application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Contact Us | Payment | Y | R1/PH-2 | 6 Hrs | M | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Process | Approved | Olive Yew | 2023-12-23
27 | REQ-110823-RSC-BUS-RLS-3.1 | Liza Doolittle | 2023-11-23 | Individuals eligible for senior care services must be aged 60 or above | The user should be aged 60 or above in order to use this application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 5 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-24
28 | REQ-110823-RSC-BUS-RLS-3.2 | Liza Doolittle | 2023-11-23 | Exceptions may be considered on a case-by-case basis for individuals aged 55-59 based on specific health or caregiving needs | The system has options for consider exception for individual aged between 55 to 59 baseball there are specific health and caregiving needs | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 4 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-25
29 | REQ-110823-RSC-BUS-RLS-3.3 | Liza Doolittle | 2023-11-23 | Prospective senior care recipients must undergo a health assessment to determine their physical and mental health status | The system should have the health assessment of each user using the senior care application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-2 | 6 Hrs | L | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-26
30 | REQ-110823-RSC-BUS-RLS-3.4 | Liza Doolittle | 2023-11-23 | Financial means tests will be conducted to assess the financial eligibility of individuals for subsidized or discounted senior care services | The system has a predefined financial taste for the financial eligibility of each users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-2 | 7 Hrs | L | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-27
31 | REQ-110823-RSC-BUS-RLS-3.5 | Liza Doolittle | 2023-11-23 | Individuals with a primary caregiver will be given priority for senior care services | The system has a priority option for caregivers to service senior care | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Services | Y | R1/PH-2 | 4 Hrs | L | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-28
32 | REQ-110823-RSC-BUS-RLS-3.6 | Liza Doolittle | 2023-11-23 | Senior care applicants must provide relevant medical documentation, including recent medical reports and any diagnoses | The relevant medical documentation including recent medical reports and any diagnosis report must be considered before using the senior care application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | - | Y | R1/PH-2 | 3 Hrs | L | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-29
33 | REQ-110823-RSC-BUS-RLS-3.7 | Liza Doolittle | 2023-11-23 | Eligibility for senior care services will be regularly reassessed at predetermined intervals to ensure that services are provided to those who continue to meet the criteria | The system will check their eligibility at predetermined intervals to ensure that they want to continue for senior care services in order to meet the criteria | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 6 Hrs | L | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Business Rules | Approved | Olive Yew | 2023-12-30
34 | REQ-110823-RSC-ERR-MSG-4.1 | Liza Doolittle | 2023-11-23 | Users should get this error message "Please complete all required fields before submitting the form." when all required fields are not filled | This error message suggests that the user need to fill all the requirement fields listed on this application | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 5 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Error Message | Approved | Olive Yew | 2023-12-31
35 | REQ-110823-RSC-ERR-MSG-4.2 | Liza Doolittle | 2023-11-23 | Users should get this error message "Please enter a valid [field] (e.g., numeric values only)." when they enter wrong field | This error message suggests that user has entered an invalid field | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 4 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Error Message | Approved | Olive Yew | 2024-01-01
36 | REQ-110823-RSC-ERR-MSG-4.3 | Liza Doolittle | 2023-11-23 | Users should get this error message "Invalid username or password. Please try again." when the username or password is not valid | This error message suggests that the username or password is invalid That username to check the username or password | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | Create/Update Profile | Y | R1/PH-1 | 6 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Error Message | Approved | Olive Yew | 2024-01-02
37 | REQ-110823-RSC-ERR-MSG-4.4 | Liza Doolittle | 2023-11-23 | Users should get this error message "Unable to connect to the server. Please check your internet connection and try again." when the website cannot establish a connection to the server | This error message suggests that user is not currently connected to the Internet | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-1 | 7 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Error Message | Approved | Olive Yew | 2024-01-03
38 | REQ-110823-RSC-ERR-MSG-4.5 | Liza Doolittle | 2023-11-23 | Users should get this error message "Your session has timed out. Please log in again to continue." when they are inactive for a long time | This error message pops up when a user is inactive for a long time and needs to refresh the page | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-1 | 4 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Error Message | Approved | Olive Yew | 2024-01-04
39 | REQ-110823-RSC-FUNC-5.1 | Liza Doolittle | 2023-11-23 | A calendar system for scheduling appointments for senior care services. | The system has a calendar for scheduling appointments for Users to use senior care services | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Appointments | Y | R1/PH-2 | 3 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Business | Functionality | Approved | Olive Yew | 2024-01-05
40 | REQ-110823-RSC-FUNC-5.2 | Liza Doolittle | 2023-11-23 | Detailed listings of available senior care services, including home care, nursing facilities, and assisted living options. | The system has detailed listings of various services such as senior cancer services including home care and nursing facilities and assisted living options for users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Services | Y | R1/PH-3 | 6 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-06
41 | REQ-110823-RSC-FUNC-5.3 | Liza Doolittle | 2023-11-23 | Information on each service, including features, costs, and user reviews | The system should show the including feature cost and the user review of each services listed for users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Services | Y | R1/PH-3 | 5 Hrs | M | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-07
42 | REQ-110823-RSC-FUNC-5.4 | Liza Doolittle | 2023-11-23 | A search function allowing users to find specific senior care services. | The system has a search bar for users to find specific senior care services | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Telehealth Integration | Health-related | Y | R1/PH-2 | 4 Hrs | M | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-08
43 | REQ-110823-RSC-FUNC-5.5 | Liza Doolittle | 2023-11-23 | Filters for refining search results based on location, type of care, and other relevant criteria. | The system has a set of filter for refining search options for users based on location type of query and the other relevant criteria | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Health-related | Y | R1/PH-2 | 6 Hrs | M | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-09
44 | REQ-110823-RSC-FUNC-5.6 | Liza Doolittle | 2023-11-23 | A system for users to leave reviews and ratings for different senior care services. | The system should have options for users to leave reviews and ratings for each senior cash services they used | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Contact Us | About Us | Y | R1/PH-3 | 7 Hrs | M | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-10
45 | REQ-110823-RSC-FUNC-5.7 | Liza Doolittle | 2023-11-23 | Messaging or chat functionality to facilitate communication between users, caregivers, and service providers. | The system should have chat options for caregivers and service providers to communicate with users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Contact Us | Contact Us | Y | R1/PH-3 | 4 Hrs | H | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-11
46 | REQ-110823-RSC-FUNC-5.8 | Liza Doolittle | 2023-11-23 | Emergency contact features for quick communication during critical situations. | The system should show the emergency contact features for quick communication during critical situation on the screen | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Contact Us | Contact Us | Y | R1/PH-3 | 3 Hrs | H | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-12
47 | REQ-110823-RSC-FUNC-5.9 | Liza Doolittle | 2023-11-23 | Secure integration with electronic health records (EHR) for easy access to medical history | The system should have a secure integration with electronic health records (EHR) for users to access their medical history | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Health | Health-related | Y | R1/PH-3 | 6 Hrs | M | H | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-13
48 | REQ-110823-RSC-FUNC-5.10 | Liza Doolittle | 2023-11-23 | Secure user authentication and authorization mechanisms | The system should have a secure user application authorization mechanism for smoother transactions | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | Login | - | Y | R1/PH-2 | 5 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Functional | Functionality | Approved | Olive Yew | 2024-01-14
49 | REQ-110823-RSC-NFUNC-6.1 | Liza Doolittle | 2023-11-23 | The website should load within a specified time frame (e.g., 3 seconds) to ensure a smooth user experience. | The system should have a smooth user experience for websites to load within a specified time frame e.g., seconds | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 4 Hrs | H | L | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Non - Functional | Performance | Approved | Olive Yew | 2024-01-15
50 | REQ-110823-RSC-NFUNC-6.2 | Liza Doolittle | 2023-11-23 | The system should be able to handle an increasing number of users and data without a significant decrease in performance. | The system should handle large numbers of user traffic without decreasing performance | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 6 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Non - Functional | Performance | Approved | Olive Yew | 2024-01-16
51 | REQ-110823-RSC-NFUNC-6.3 | Liza Doolittle | 2023-11-23 | The interface should have a consistent design and layout to facilitate easy navigation for seniors. | The website should have a consistent design and layout to facilitate an easy navigation for users | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 7 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Non - Functional | Performance | Approved | Olive Yew | 2024-01-17
52 | REQ-110823-RSC-NFUNC-6.4 | Liza Doolittle | 2023-11-23 | The website should be available 24/7, with minimal downtime for maintenance or updates. | The system should be available 24 by 7 with a minimal downtime for maintenance or updates | Holly Golightly | Joseph Arimathea | Reimagined Senior Care | - | - | Y | R1/PH-2 | 4 Hrs | H | M | Mary Magdalene | Allie Grater | Teri Dactyl | N | - | Non - Functional | Performance | Approved | Olive Yew | 2024-01-18